## Estimates - EMM
Stages
Staff
| Planning (2 weeks) | Analysis (3 weeks) | Design (3 weeks) | Development (3 weeks) | Testing (1 week)
Project Manager | 40.0 hours* 2 weeks | 40.0 hours* 3 weeks | 40.0 hours* 2 weeks
Project Researcher | 40.0 hours* 2 weeks | 40.0 hours* 3 weeks | 40.0 hours* 2 weeks
Database Analyst |  | 40.0 hours* 3 weeks | 40.0 hours* 3 weeks | 40.0 hours* 2 weeks
Web Developer |  | 40.0 hours* 3 weeks | 40.0 hours* 3 weeks | 40.0 hours* 3 weeks
Mobile Developer |  | 40.0 hours* 3 weeks | 40.0 hours* 3 weeks | 40.0 hours* 3 weeks
Quality Assurance |  | 40.0 hours* 2 weeks | 40.0 hours* 1 week |  | 40.0 hours* 1 week
Total Time | 160 hours | 680 hours | 560 hours | 320 hours | 40 hours